## Slide 1: ctcLink Project Review
for
TSB Portfolio/Policy Subcommittee
February 11, 2016
Michael Scroggins, Deputy Executive Director, SBCTC

## Slide 2: Background
Strategic Technology Plan
Project Principles
System Readiness Assessment
HB 1909
COP $50M
Budget $100M / Schedule 5YR
Private Cloud Oracle/PeopleSoft Applications
Ciber – Implementation Contractor
Moran and Associates – External QA

## Slide 3: Schedule
 | Original | Actual
Contract | 01/2013 | 01/2013
Global Design | 10/2013 | 10/2014
Pilot Phase | 08/2014 | 08/2015
Wave One | 08/2015 | 11/2016*
Wave Two | 08/2016 | TBD
Wave Three | 08/2017 | TBD

## Slide 4: Budget
Original Project Budget - $100M
  Software Licenses
  Cloud Managed Services
  Contract Deployment Services
  Project Staff
Estimated Expenditure January 2016 - $83M
Actual Expenditure January 2016 - $73M
Projected Project Budget - $110M

## Slide 5: Pilot Status
Stabilization phase
Staff continuing to adapt to new systems and business process changes
Winter quarter much better than fall
31K active student accounts
13K average logins on weekdays

## Slide 6: Lessons Learned
Data Conversion
Payroll Business Process
General Ledger Crosswalk
External Systems Interfaces
Individual Access/Security
Data Services & Reporting
Training/Change Management

## Slide 7: Going to Scale
Master Configuration Exists
Common General Ledger
Common Coding and Naming
Methodology Changes
Training/Business Processes
Data Services & Reporting
College Ownership

## Slide 8: QUESTIONS?