## Slide 1: Migration to Mainframe as a Service (MFaaS)
MFaaS Steering Committee Meeting
December 17, 2020

## Slide 2: Agenda
Production Issues
  Slowness issues identified by LNI, OFM and DSHS
  FTP Latency
Decommission of Equipment
  Olympia
  Philadelphia
Lessons Learned
Remaining Items
  Updated Terms of Service (TOS)
  Consolidation of web pages
Q&A
2

## Slide 3: Production Issues (Omaha)
File Transfers
  IBM acknowledges this issue and is developing a fix
    Authorized Program Analysis Report (APAR) exists
    To become a Program Temporary Fix (PTF)
Slow Performance that impacted production on Tuesday
  Caused by misconfigured capacity management that limited available resources

## Slide 4: Decommission of equipment
Olympia (Former Production)
  When do we decommission the equipment in Olympia?
  Data will be destroyed via NIST 800-88 (data sanitation) once go ahead is given to Ensono
  z12
  Data Storage (DLM and Virtual Tape)
  Network switches
Philadelphia (Disaster Recovery)
  Only have 1 DLM to decommission

## Slide 5: Lessons Learned
Lessons Learned
  Will be sending out a survey to all SC members and Testing Team
    What Went Well?
    What Didn’t Go So Well?
    What Are the Key Takeaways for Future Projects?
    What Needs Improvement?

## Slide 6: Items Remaining
Creation of Updated Terms of Service (TOS)
Consolidation of Web Pages for Mainframe Services

## Slide 7: Thank you
Final Testing Customer Group meeting is scheduled for December 23rd
Next Customer Group meeting is scheduled for January 5th
  Meetings are held semi-monthly (first and third Tuesday of the month)
Next SC meeting is not currently scheduled
  Should we schedule for January 12?
  How far out should we schedule meetings?
Project documentation location:
https://teams.microsoft.com/_#/files/Project%20Management?threadId=19%3A82209f304c424891b99b82a42bb6bb1a%40thread.skype&ctx=channel
7

## Slide 8: Questions and Answers

## Slide 9: Appendix

## Slide 10: Pricing Model
Description | Price Element
CPU Consumption (CPU hours used in month) | $160 / CPU hour
Reserved Capacity for Dedicated LPARs | $26,000 per LPAR
Virtual Tape | $0.30 / GB
DASD | $1.70 / GB
Notes: Current storage pricing: Online Disk $1.387 / GB / mo
Virtual Tape $1.022 / GB / mo