## Slide 1: Migration to Mainframe as a Service (MFaaS)
MFaaS Steering Committee Meeting
December 8, 2020

## Slide 2: Agenda
Testing Results
Risks
Production Cutover
Go / No-Go Input
Disaster Recovery
Q&A
2

## Slide 3: Testing Results
All mock testing and DR Validation data as of 12/6
 | Mock Testing |  |  |  | FTP Info | 
 | # of Test Cases | Successful | Unsuccessful | % Complete | Uses FTP | File Size
DCYF | 5 | 5 | 0 | 100% | Yes | 50 MB
DES | 16 | 16 | 0 | 100% | No | N/A
DNR | 93 | 92 | 1 | 99% | No | N/A
DRS | 47 | 47 | 0 | 100% | Yes | <100 MB
DSHS | 33 | 33 | 0 | 100% | Yes | 437 MB
ECY | 0 | N/A | N/A | 100% | Yes | 15 MB
ESD | 198 | 198 | 0 | 100% | Yes | 239 MB
HCA | 11 | 10 | 1 | 91% | Yes | 176 MB
L&I | 145 | 142 | 2 | 98% | Yes | 100 GB
OFM | 91 | 91 | 0 | 100% | Yes | 1.25 GB
TRE | 5 | 5 | 0 | 100% | Yes | <1 MB
WaTech | 17 | 17 | 0 | 100% | Yes | <100 MB

## Slide 4: Outstanding Risks
File Transfer
  File transfers taking 2.5x longer
  Need to understand from LNI what time do your jobs finish today?
    What is the impact of FTP jobs taking longer?
App License issues
  QuickRef (Chicago Soft)
    Agreement signed with Chicago Soft
  Star Tool and Comparex (Serena / Micro Focus)
    Per discussions with LNI and OFM, not a major concern if not available day 1
        Need by end of week 1
    WaTech has signed the contract with Serena/Micro Focus, awaiting counter signature, before PO can be issued

## Slide 5: Mock Testing and Production Cutover Timeline
Production Cutover Scheduled Start Time: December 13 @ 2:00am
  DSHS/Aces team to inform when their job completes
Ensono production migration duration: 4-5 hours
Ensono / WaTech environment checks: 1 hour
Agency Environment Readiness Validation: 6 hours

## Slide 6: Go / No-Go Decision by Agency FINAL DECISION = GO
 | Go / No-Go Decision
DCYF | 
DES | Go
DNR* | Go
DRS* | Go
DSHS* | Go
ECY | Go
ESD | Go
HCA | Go
L&I* | Go
OFM* | Go
TRE | Go
WaTech* | Go
Ensono* | Go
OCIO* | Go
DCYF did not provide a representative authorized to make the Go/No-Go decision at the meeting
* = Agencies or Entities represented on the Steering Committee

## Slide 7: Disaster Recovery
DR Validation results:
Full DR Test
  Need to schedule for Q1 2021
  Will want all agencies participation
DR Validation |  |  |  | 
Agency | # of Test Cases | Successful | Unsuccessful | % Complete
DCYF | 8 | 8 | 0 | 100%
DES | 14 | 14 | 0 | 100%
DNR | 27 | 27 | 0 | 100%
DRS | 16 | 16 | 0 | 100%
DSHS | 0 | 0 | 0 | 100%
ECY | 0 | N/A | N/A | 100%
ESD | 10 | 10 | 0 | 100%
HCA | 0 | 0 | 0 | 100%
LNI | 0 | 0 | 0 | 100%
OFM | 5 | 5 | 0 | 100%
TRE | 5 | 5 | 0 | 100%
WaTech | 1 | 1 | 0 | 100%
 | 86 | 86 | 0 | 100%

## Slide 8: Thank you
Next Customer Group meeting is scheduled for December 15th
  Meetings are held semi-monthly (first and third Tuesday of the month)
Next SC meeting is not currently planned
Project documentation location:
https://teams.microsoft.com/_#/files/Project%20Management?threadId=19%3A82209f304c424891b99b82a42bb6bb1a%40thread.skype&ctx=channel
8

## Slide 9: Questions and Answers

## Slide 10: Appendix

## Slide 11: RAID Log
Risk Category | Risk | Date Raised | Assigned To | Status | Risk Mitigation/Response Plan
Licenses | Several products are failing in mock testing due to license expiration or authorization code issues | 11/2/2020 | Ensono/LC/NC | Open | Ensono is currently working with Donna Beatty and SW vendors on getting appropriate temp authorization codes. Create tasks for each of the SW licenses that will expire in December. Including: requesting the license from the vendor, receiving the licenses from the vendor, installing the license in Production/DR, verifying the application starts up with no issues.
Communication | Interface between vendor resources is inconstant. Information and decisions are at times conflicting. Falling short of full alignment and synchronization could result in miscommunication, missed steps, and errors. | 11/10/2020 | Ensono | Open | Ensono to be more detailed in their communication both between their silos and with WaTech.
Testing | FTP is taking longer to complete than previously in Olympia (up to 3x longer) | 11/10/2020 | Ensono/LC/NC | Open | Ensono working to identify why the FTP process is taking longer. WaTech working with agencies to understand the potential impact.
Disaster Recovery | Need to ensure the DR site is adequate and to test the FTP throughput. | 11/20/2020 | Ensono/LC/NC | Open | Ensono needs to create sufficient test plans in order to fully test all aspects of the DR (Downers Grove) environment, including failover to the environment, FTP to/from, SW licenses, etc.