## Slide 1: Migration to Mainframe as a Service (MFaaS)
MFaaS Steering Committee Meeting
November 24, 2020

## Slide 2: Agenda
Testing Update
Production Cutover
  RAID Log Review
Key Activities
Q&A
2

## Slide 3: Testing Update
 | Mock Testing |  |  |  |  |  | DR Testing |  |  |  | 
 | Testing Status | # of Test Cases | Successful | Unsuccessful | % Complete |  | Testing Status | # of Test Cases | Successful | Unsuccessful | % Complete
DCYF | Complete | 5 | 5 | 0 | 100% |  | Complete | 8 | 8 | 0 | 100%
DES | Complete | 0 | 0 | 0 | 100% |  | Complete | 0 | 0 | 0 | 100%
DNR | In Process | 93 | 92 | 1 | 99% |  | Complete | 27 | 27 | 0 | 100%
DRS | In Process | 47 | 45 | 0 | 96% |  | In Process | 16 | 0 | 0 | 0%
DSHS | Complete | 33 | 33 | 0 | 100% |  | Complete | 0 | 0 | 0 | 100%
ECY | N/A | 0 | N/A | N/A | 100% |  | N/A | 0 | N/A | N/A | 100%
ESD | In Process | 200 | 160 | 0 | 80% |  | Complete | 10 | 10 | 0 | 100%
HCA | In Process | 11 | 10 | 1 | 91% |  | Not Started |  |  |  | #DIV/0!
L&I | In Process | 145 | 99 | 3 | 68% |  | Not Started |  |  |  | #DIV/0!
OFM | In Process | 91 | 71 | 1 | 78% |  | Complete | 5 | 5 | 0 | 100%
TRE | Complete | 5 | 5 | 0 | 100% |  | Complete | 4 | 4 | 0 | 100%
WaTech | Complete | 17 | 17 | 0 | 100% |  | In Process | 1 | 0 | 0 | 0%
TOTAL |  | 647 | 537 | 5 | 83% |  |  | 70 | 54 | 0 | 77%
All mock testing and DR Validation data as of either 11/20 or 11/23

## Slide 4: Testing Issue Log
Issues Overview
File Transfer
  File transfer taking 3x longer (investigating the potential implications)
  Ensono currently investigating packets
  OFM & LNI have firewall issues they are working to resolve
App License issues
  Currently have an issue with QuickRef (Chicago Soft), issue for DNR/HCA
    Under review by OLS
  Need to review the licenses that will be updated during cutover
Item | Reported | App | Owner | Tester | Issue | Remediation
31 | 11/10 | FTP | Ensono | (Joint testing in progress) | FTP from Olympia to Omaha seems to be running twice as long as it does normally. | 11/23 - Mutual Trace collected with LNI Network/Interface data. Files in process of being posted for Ensono Analysis. 11/24 meeting scheduled to review data 11/19 - Mutual Trace captured. 9:30am Pacific. LNI Packet Trace needs to include Network/Interface data. 11/23 - 9am Pacific meeting to retest 11/17 - 12:53 large (LNI) FTP currently running with joint capture. Another job for USBank being recorded 11/17 - Ensono Analyze Trace Data collected on 11/16. HW Config reconciled for Olympia and Omaha. Joint Ensono/WaTech trace may be needed pending trace analysis. 11/16 - Further FTP Testing at 1pm PST. Breton ran a trace, trace data being analyzed. The connectivity from the Distributed servers to the mainframe in Olympia is 10GB. The circuit from Olympia to Omaha is only 1 GB. Some differences are to be expected. Ensono verified Circuit not 100% utilized during 11/10 evening testing. 11/13 - Testing will continue on Monday, 11/16. Size and Memory of the testing box not the issue based on 11/13 testing. Circuit and Routers not the issue as mutually agreed 11/13. 11/16 Testing by WaTech showed job completed in 18 min similar to Prod.
7 | 11/2 | QuickRef | Ensono/WaTech |  | License Key error | 11/23 - WaTech received a quote. 11/17 - WaTech Legal working to resolve with Chicago-Soft Still do not have new key from ChicagoSoft. WaTech and Ensono working with vendor. Pendng a decision if SW is required at this point. Donna
50 | 11/20 | FTP | WaTech | Carolee (LNI) | Access to IP addresses: 159.1.251.188, 159.1.251.189, and 159.1.94.227 | 11/23 - Theissue with 159.1.94.227 has been resolved.. .188 and .189 are still outstanding. 11/20 checking firewall permissions (Dave) .188 and .189 servers are for Enterprise Extender traffic with the NET1 LPAR on UDP port 12000-12004 and are open. Source 10.81.134.221 / 147.55.117.199 to 159.1.94.227, port 21
51 | 11/20 | FTP | WaTech | Randy J (OFM) | Access to 198.238.122.207 via port 1416 from Mock2 MQA1 | 11/23 - Waiting to be tested. LNI MQA2 test was successful. 11/20 - Checked firewalls ok for port 1415 and 1416 per Dave Wilbur, check OFM Agency firewall for same
52 | 11/23 | Barr Printers | WaTech | Jason Johnson | Unable to access / start Barr printers RMT(13), RMT(58) | 11/23 - Researching MF Firewall and LPAR access - Currently waiting on agencies.

## Slide 5: Mock Testing and Production Cutover Timeline
2-Nov | 3-Nov | 4-Nov | 5-Nov | 6-Nov |  | 
Mock 1 Testing - Completed |  |  |  |  |  | 
9-Nov | 10-Nov | 11-Nov | 12-Nov | 13-Nov |  | 
Mock 2 Testing - Completed |  |  |  |  |  | 
16-Nov | 17-Nov | 18-Nov | 19-Nov | 20-Nov |  | 
Mock 2 Testing - Completed |  |  |  |  |  | 
Ensono DR Prep - Completed |  | DR Validation - Completed |  |  |  | 
23-Nov | 24-Nov | 25-Nov | 26-Nov | 27-Nov |  | 
Optional Mock 2 Testing – In Process |  |  | Holidays |  |  | 
Optional DR Validation – In Process |  |  |  |  |  | 
30-Nov | 1-Dec | 2-Dec | 3-Dec | 4-Dec |  | 
Mock 3 Testing |  |  |  |  |  | 
7-Dec | 8-Dec | 9-Dec | 10-Dec | 11-Dec | 12-Dec | 13-Dec
Cutover Prep |  |  |  |  | Production Cutover | 
Go/No-Go meeting scheduled w/non-SC agencies – Dec 7
Go/No-Go meeting with SC on Dec 8
Production Cutover Start Time: December 13 @ 12:01am
  Might need to be moved to 2:00am start

## Slide 6: RAID Log
Risk Category | Risk | Date Raised | Assigned To | Status | Risk Mitigation/Response Plan
Licenses | Several products are failing in mock testing due to license expiration or authorization code issues | 11/2/2020 | Ensono/LC/NC | Open | Ensono is currently working with Donna Beatty and SW vendors on getting appropriate temp authorization codes. Create tasks for each of the SW licenses that will expire in December. Including: requesting the license from the vendor, receiving the licenses from the vendor, installing the license in Production/DR, verifying the application starts up with no issues.
Communication | Interface between vendor resources is inconstant. Information and decisions are at times conflicting. Falling short of full alignment and synchronization could result in miscommunication, missed steps, and errors. | 11/10/2020 | Ensono | Open | Ensono to be more detailed in their communication both between their silos and with WaTech.
Testing | FTP is taking longer to complete than previously in Olympia (up to 3x longer) | 11/10/2020 | Ensono/LC/NC | Open | Ensono working to identify why the FTP process is taking longer. WaTech working with agencies to understand the potential impact.
Disaster Recovery | Need to ensure the DR site is adequate and to test the FTP throughput. | 11/20/2020 | Ensono/LC/NC | Open | Ensono needs to create sufficient test plans in order to fully test all aspects of the DR (Downers Grove) environment, including failover to the environment, FTP to/from, SW licenses, etc.

## Slide 7: Key Activities
Production Go/No-Go Checklist
  Received responses from DNR, DRS, DSHS, HCA, LNI, TRE & WaTech
  Still waiting on DCYF, DES, ESD & OFM
  Need to identify how long agencies will need to complete their testing
SSA Approval
  Received the written approval letter from SSA on Friday 11/20
Contingency Date – January 16-17
  Alternate contingency date in Q1 2021 might be discussed at the next SC per request from LNI

## Slide 8: Questions and Answers

## Slide 9: Thank you
Next Customer Group meeting is scheduled for December 1th
  Meetings are held semi-monthly (first and third Tuesday of the month)
Next SC meeting is planned for December 8th at 2pm
  Will include a Go/No-Go discussion for the production cutover
Project documentation location:
https://teams.microsoft.com/_#/files/Project%20Management?threadId=19%3A82209f304c424891b99b82a42bb6bb1a%40thread.skype&ctx=channel
9

## Slide 10: Appendix

## Slide 11: Ensono Calendar