## Slide 1: Migration to Mainframe as a Service (MFaaS)
MFaaS Steering Committee Meeting
October 29, 2020

## Slide 2: Agenda
Data Replication
Timeline
Production Cutover
Production Cutover Checklist
Contingency Dates
Q&A
2

## Slide 3: Data Replication Update
Disk (DASD) Replication completed on Monday (Oct 26)
Virtual Tape Replication started on Monday (Oct 26)
  Ensono estimate to complete: ~6.5 days
  Should finish approximately Sunday, November 1

## Slide 4: Mock Testing and Production Cutover Timeline
2-Nov | 3-Nov | 4-Nov | 5-Nov | 6-Nov |  | 
Mock 1 Testing |  |  |  |  |  | 
9-Nov | 10-Nov | 11-Nov | 12-Nov | 13-Nov |  | 
Mock 2 Testing |  |  |  |  |  | 
16-Nov | 17-Nov | 18-Nov | 19-Nov | 20-Nov |  | 
Mock 2 Testing |  |  |  |  |  | 
DR Validation |  |  |  |  |  | 
23-Nov | 24-Nov | 25-Nov | 26-Nov | 27-Nov |  | 
 |  |  | Holidays |  |  | 
30-Nov | 1-Dec | 2-Dec | 3-Dec | 4-Dec |  | 
Mock 3 Testing |  |  |  |  |  | 
7-Dec | 8-Dec | 9-Dec | 10-Dec | 11-Dec | 12-Dec | 13-Dec
Cutover Prep |  |  |  |  | Production Cutover | 

## Slide 5: Production Cutover
Option 1 – Start on Saturday, December 12
  Begin in the AM on Saturday
  Provides both Saturday and Sunday to complete the migration and address any issues
Option 2 – Start on Sunday, December 13
  Begin during the maintenance window 12:01am PT
  Would allow any jobs scheduled to run on Saturday to complete prior to beginning the migration
  Only have Sunday to complete migration and address any issues that arise

## Slide 6: Production Cutover Checklist
Production cutover checklist sent yesterday
  Outlines the tasks that will be completed by Ensono and WaTech post migration
  If these tasks fail and we are unable to resolve within the cutover window would need to fallback to Olympia Mainframe
Need each agency to create their Production Go/No-Go checklist

## Slide 7: Contingency Cutover Dates
Can DNR and LNI make January 16-17 work for a contingency cutover date?
If not, what date can be agreed upon?
Saturday | Sunday
2-Jan | 3-Jan
1 agency - not acceptable | 
9-Jan | 10-Jan
1 agency - Acceptable | 
16-Jan | 17-Jan
3 agencies - Acceptable | 
23-Jan | 24-Jan
1 agency - Acceptable 1 agency - not acceptable | 
30-Jan | 31-Jan
6-Feb | 7-Feb
13-Feb | 14-Feb
20-Feb | 21-Feb
1 agency - Acceptable (3rd choice) | 
27-Feb | 28-Feb
1 agency - Acceptable (1st choice) | 
6-Mar | 7-Mar
13-Mar | 14-Mar
1 agency - Acceptable (2nd choice) | 
Agency | 1st Choice | 2nd Choice | 3rd Choice | Unacceptable
DNR | 23-Jan |  |  | 
DRS | 16-Jan | 9-Jan |  | 2-Jan 23-Jan
DSHS | 16-Jan |  |  | 
LNI | 27-Feb | 13-Mar | 2-Feb | 
OFM | 16-Jan |  |  | 

## Slide 8: Questions and Answers

## Slide 9: Thank you
Mock 1 Testing starts Monday, November 2
Next Customer Group meeting is scheduled for November 3rd
  Meetings are held semi-monthly (first and third Tuesday of the month)
Next SC meeting is planned for November 10th at 2pm
Project documentation location:
https://teams.microsoft.com/_#/files/Project%20Management?threadId=19%3A82209f304c424891b99b82a42bb6bb1a%40thread.skype&ctx=channel
9