## LAM RACI
RACI Matrix - RSA NetWitness SIEM
R - Those who do the work to achieve the task. May delegate others.
A - One who is ultimately answerable for the correct and thorough completion of the work
C - Those whose opinions are sought - there is two-way communication
I - Those who are kept up to date on progress - there is only one-way communication | Work Group
Responsibility | WaTech InfoSec | WaTech Infrastructure | WaTech NSD | OCS | RSA | MSSP | WA Agency Customer | Comments
Administration
Create AD groups | AC |  |  |  |  | C | AR
Assign AD groups to agencies | AC |  |  |  |  | R | I
Add / remove users from AD groups | C | [5 empty] | AR
Manage SA Advanced Settings | AC |  |  |  |  | R | C
Modify ESA Settings | AC |  |  |  |  | R | C
Add Event Sources to SIEM | C |  |  |  |  | C | AR
Modify Hosts to communicate with SIEM | C |  |  |  |  | C | AR
Manage Netwitness
View and Manage Incidents | AR |  |  | AR |  | AR | AR
Create and Manage Reports | [5 empty] | C | AR
Create and Manage Alerts | [5 empty] | C | AR
Create and Manage Rules | [5 empty] | C | AR
Create and Manage Dashboards | [5 empty] | C | AR
Infrastructure Configuration and Maintenance
Install ESXi | AC |  |  |  | R
Configure ESXi network settings | AC |  |  |  | R
Maintain and update ESXi | A |  |  |  |  | R
Virtual Server Creation | A |  |  |  | R
Configure pre-query for each agency | A |  |  |  | R
Configure SGN SIEM network and firewalls | A |  | R
Configure agency SIEM network and firewalls | C |  |  |  | C |  | R
Monitor and manage physical appliances | AR |  |  |  |  | C
Change Management
Change Management per WaTech Requirements | AR |  |  |  |  | C | C
Change Management per Agency Customer Requirements | C |  |  |  |  | C | AR
Change Management per MSSP Requirements | C |  |  |  |  | RA | C
Support
Single Point of Contact to Initiate Troubleshooting with SGN Network and Firewalls | AR |  |  |  |  | I | I
Single Point of Contact to Initiate Troubleshooting Netwitness Platform Issues | AR |  |  |  |  | I | I
Single Point of Contact to Initiate Troubleshooting of Netwitness issues for agencies | AR |  |  |  |  | I | I
Troubleshooting Problems with SGN Network and Firewalls | AC |  | R |  |  | C | I
Troubleshooting Netwitness questions for Agencies | AC |  |  |  |  | R | I
Performance Monitoring
ESXi performance monitoring | A |  |  |  |  | R
Virtual Server Performance Monitoring | A |  |  |  |  | R | I
Monitor EPS use by agencies | AR |  |  |  |  | C | I
Netwitness Performance Monitoring | A |  |  |  |  | R | I
Netwitness Health & Wellness Monitoring | A |  |  |  |  | R | I
System Documentation
Documentation of ESXi Infrastructue | C |  |  |  | R | I
Documentation for adding data sources to the SIEM | AC |  |  |  | R | C | I
Documentation of Agency onboarding Procedures | AR |  |  |  | C | c | I
Infrastructure Security
Maintain SIEM Firewall Rulesets | AC |  | R |  |  | C
Maintain Agency Firewall Rulesets to support virtual stack | AC |  |  |  |  | C | AR
Configure ESXi according to industry hardening standards | A |  |  |  | R | I
Configure Netwitness appliance according to industry hardening standards | A |  |  |  | R | I
Acquisitions
Acquire NetWitness EPS pool | AC | R |  |  | C | I
Acquire MSSP services | AC | R |  |  | C | C
Acquire and Manage ESXi licenses | AC | R |  |  | C | I
Acquire Netwitness modules not included with Logging and Monitoring service | C |  |  |  | C |  | AR