## Recommendations and Response
For QA Findings / Other | [7 empty] | For Agency Response
ID | Date Opened | Date Closed or Cancelled | Status | Type | Description | QA Recommendation | Impact | Owner/Responsibility | Action | Status Update | Date Action Will Complete | Date Action Completed
1 | 2024-06-01 |  | Open / In Progress / Closed / Cancelled | Issues / negative finding / Risk | Project does not have full understanding of impacted stakeholders and degree of change impact for readienss. | Project should complete internal and external stakeholder analyses, document impact and include these in orgnanization change management plan and training plan to support readiness and adoption. | High / Moderate / Low | OCM Lead | Conduct overall stakeholder analysis and document impact into OCM plan and Training Plan. | 6/1/24 - Completed list of stakeholders. 7/1/24 - Completed initial draft of stakeholder analysis. Pending final review by Sponsor | 7/1/24 8/15/24
ID | Date Opened | Date Closed or Cancelled | Status | Type | Description | QA Recommendation | Impact | Owner / Responsible Parties | Action | Status Update | Date Action Will Complete | Date Action Will Complete
Note on J2: States the overall action planned.
Note on K2: Gives updates against the stated action if it spans reporting periods.
Note on L2: Keep running log of planned date.
Note on M2: Specifies when it was reported complete by the agency (separate from QA closing date)