## Sheet1
IT Investment Intake
The IT Investment Intake Tool is used to assist Washington state agencies and WaTech in assessing the cost, duration, complexity, and statewide significance of an anticipated information technology project (RCW 43.105.245).
Agencies are required to submit every IT investment/project with a combined level of effort total cost of more than $500,000 - OR - a duration longer than six months through this tool. Submitted project data is retained and will be used for analysis and refinement of oversight policies, practices and the tool itself.
Please answer to the best of your ability with the most accurate information available at the time of submission. Comments are not required but are encouraged for clarification purposes.
Note: This intake tool assesses the level of risk for your IT investment or project. This assessment is based on the Investment Information you provide, and will determine whether you need to answer some or all of the Tiering Assessment questions.
DISCLAIMER: This form is only to be used offline for prep work and will not be accepted in place of online submission. You must submit your actual IT Investment Intake form through our online portal located at:
https://watech.wa.gov/strategy/state-it-projects/it-investment-intake
Select Agency*
Investment Name*
Primary Point of Contact Name*
First Name
Last Name
Primary Point of Contact Email Address*
Alternate POC Name*
First Name
Last Name
Alternate POC Email Address*
Primary Point of Contact Phone Number*
Alternate POC Phone Number*
Investment Information
Investment Description*
Investment Type*
Network and Telecommunications
Data Center
Cloud Services
Data Management & Analytics
IT Security
Privacy & Data Protection
Geospatial / GIS
System Integration
Websites & Web Portals
Other
Investment State*
Feasibility Study
New Implementation
Renewal
M&O
Investment Solution*
Software
Hardware
Estimated Investment Budget*
Is your investment subject to Section 701?*
Yes
No / Unsure
Does this investment include any system that has administrative or financial business function component as defined by WaTech policy 122?*
Yes
No
# | Question | Response
1 | Estimated Investment Budget | Under $500K.
Between $500K and $1M.
Between $1M and $5M.
Between $5M and $10M.
Between $10M and $50M.
Over $50M.
# | Question
2 | Duration | Less than 6 months.
6 to 12 months.
12 to 24 months.
24 to 36 months.
More than 36 months.
# | Question
3 | How many people are required to complete this project at its peak activity? | Up to 5 people.
6 to 10 people.
11 to 25 people.
26 to 50 people.
More than 50 people.
# | Question
4 | How many deployments will this project have? | Phased deployment.
Single deployment.
# | Question
5 | Which of the options best describe the project’s funding? | All funding is confirmed.
Not all funding is confirmed, but funding is expected to be confirmed before needed.
Not all funds are confirmed. Internal agency dollars, grants, or federal funds will need to be identified and committed OR a funding request will need to be submitted to OFM in an upcoming budget cycle.
Funding sources are unknown, or no funding has been confirmed.
# | Question
6 | Does the system collect, process, or use sensitive or confidential data? | Only category 1 data is stored or processed.
Category 1-2 data is stored or processed.
Category 1-3 data is stored or processed.
Category 1-4 data is stored or processed.
# | Question
7 | Which of the options best describe the project’s management and governance processes, and the project manager’s experience? | The agency has documented, repeatable project management and governance processes and project managers have at least 24 months of experience leading and successfully delivering Major Projects.
The agency has undocumented or ad hoc project management and governance processes and project managers have less than 24 months of experience leading Major Projects.
The agency has undocumented or ad hoc project management and governance processes OR the project managers are inexperienced leading Major Projects.
# | Question
8 | How would you describe the size of the budget relative to other projects in your organization? | Smaller: Relatively smaller than the average size project for the agency.
Same: About the same size as an average size project for the agency.
Larger: Relatively larger than an average size project for the agency.
# | Question
9 | Are there constraints on the project schedule? | The project schedule has contingency or slack and/or is flexible.
The project schedule does not have contingency or slack, but the end date is self-imposed.
The project schedule is fixed / mandated (e.g., replacing out of support or end of life tool, legislative deadline, etc.), but there is slack or contingency built into the project schedule.
The project schedule is fixed / mandated and has no slack or contingency.
# | Question
10 | How will the proposed business outcomes of the project change how your external customers interact with the system? | There are no external customers that will use the system; or customers will see no significant impact to the way they do business with the agency.
Customers will conduct business in the same way; but use a different system to interact with the agency.
Customers will need to change their business process using a different system to interact with the agency.
# | Question
11 | Which of the options best describe the project’s impact on agency staff? | No direct impact on agency staff(0%).
Minimal impact on agency staff(up to 5%).
Low impact on agency staff(6 to 25%).
Moderate direct impact on agency staff(26 to 50%).
High direct impact on agency staff(51% or more).
# | Question
12 | Which of the options best describe the project’s impact on Washingtonians? | No direct impact on Washingtonians(0%).
Minimal impact on Washingtonians(up to 5%).
Low impact on Washingtonians(6 to 25%).
Moderate direct impact on Washingtonians(26 to 50%).
High direct impact on Washingtonians(51% or more).
# | Question
13 | Which of the options best describe the project’s impact to external (to the agency) entities / organizations? | None - No external entities will be impacted.
Low - Up to 5 external entities will be impacted.
Moderate - 5 to 10 external entities will be impacted.
High - More than 10 external entities will be impacted.
# | Question
14 | Which of the options best describe the impact if the project fails? | Loss of opportunity to implement an improvement.
Increased costs that could be avoided, will instead be incurred.
Inability to comply with standards/leading practices.
Inability to comply with policy/law/mandate.
# | Question
15 | What degree of change will be required to supporting technologies for solution implementation? | The project will require no changes to supporting technology (It is a stand-alone system).
The project will require minor changes to supporting technology.
The project will require moderate changes to supporting technology.
The project will require major changes to supporting technology.
# | Question
16 | What type of software solution will be implemented by this project? | Subscription services; SaaS/PaaS.
Lift and shift of on-premise applications to IaaS provider.
Licensed software hosted by third-party cloud provider.
Licensed software self-hosted and maintained.
Development platform used to design/build self-hosted application(s).
# | Question
17 | How many separate contracts (excluding QA, IV&V and OCM) associated with key deliverables are planned for this project? | No contracts.
Up to 1 contract.
2 to 4 contracts.
5 or more contracts.
# | Question
18 | How many agencies are involved for decision making, funding, providing resources and governance of the project? | Only involves one agency.
Involves two to three agencies.
More than three agencies.
# | Question
19 | How do you expect team workload allocation to impact project timelines? | Team members will be fully allocated to the project. Team workload presents no risk to the project timeline.
Team members are part-time on the project but have the required availability. Team workload presents minor risk to the project timeline.
Some or all of the team members are over-committed. Team workload presents serious risks to the project timeline.
# | Question
20 | Which of the options best describe the authority and experience of the project’s executive sponsor? | The project has a fully committed and engaged executive sponsor with BOTH the authority to allocate organization-wide staff and prior experience sponsoring Major Projects.
The project has a fully committed and engaged executive sponsor with authority to allocate organization-wide staff; but the sponsor has no experience sponsoring Major Projects.
The project has a fully committed and engaged executive sponsor without authority to allocate organization-wide staff but has experience sponsoring Major Projects.
The project has a fully committed and engaged executive sponsor with NEITHER the authority to allocate organization-wide staff nor experience sponsoring Major Projects.
The project does NOT have an executive sponsor fully engaged with the project.
# | Question
21 | How many Major Projects has the agency successfully delivered (e.g., on-time, on-budget) in the last five years? | More than 10 major and successful projects.
5 to 10 major and successful projects.
1 to 4 major and successful projects.
No major or successful projects.
# | Question
22 | Which of the options best describe the project’s interdependency with other projects? | This project is not dependent on another project and/or no other project is dependent on this project.
This project is dependent on one project OR one project is dependent on this project.
This project has dependencies across multiple projects but none of the projects are identified as Major Projects.
This project is dependent on another Major Project and/or another Major Project is dependent on this project.
# | Question
23 | Which of the options best describe (for this project) the system data migrations? | No migration.
All legacy data sources are known and mapped for migration.
Some (approx. 50% or more) of the legacy data sources have been identified and more work is needed for analyses and mapping.
No legacy data source identification work has been conducted.
# | Question
24 | Are project requirements clear and documented? | At least 90% of the requirements are clearly articulated and documented.
At least 50% of total requirements are clearly articulated and documented.
Less than 50% of total requirements are clearly articulated and documented.
# | Question
25 | Which of the options best describe (for this project) the system interfaces? | No interfaces needed.
All interfaces are known and are diagrammed/mapped.
Some (approx. 50% or more) of the interfaces have been identified and mapped; and more work is needed for analyses and mapping.
# | Question
26 | If the project proposes to have system interfaces (prior question), which of the options best describe (for this project) the level of interoperability? | No system interface work has been conducted.
Not-applicable (Selected if answer to prior question is 'No interfaces').
Interoperability is limited to basic integrations to move data from this system to others.
Interoperability includes moving data in and out of numerous systems that support integrated workflow that is directly related to this projects scope.
In addition to the above, Interoperability includes moving data to enterprise data management solutions to support analytics and/or feeds other indirect workflows; horizontal movement of data across the enterprise.